**Sub-recipient Name:** New Jersey Institute of Technology

**Subaward No:** 00000289

**Principal Investigator:** Matthew J. Bandelt

**LTBP TSSC – Task Order 2**

**Federal Contract # DTFH61-17-D00001**

For the Period from 7/1/2018 through 7/31/2018

# Accomplishments/Work Performed

The following is a complete account of all accomplishments and work performed on each task during this reporting period.

# Task 2: LTBP Program Strategic Research Matrices

During this period, NJIT continued to review relationships for the Strategic Research Matrices. Further investigation was conducted on different input/output relationships to help identified research initiatives and directions. The keyword list was further updated to identify relationships surrounding vehicular loading, maintenance actions, environmental conditioning, and preservations techniques.

Number of hours during this period: 47.6

# Task 3: Training Curriculum

No work was completed on this task during this period.

Number of hours during this period: 0 hours.

# Task 4: Development and Refinement of Data Collection Protocols

No work was completed on this task during this period.

Number of hours during this period: 0 hours.

# Work Anticipated During the Next Period

For the next period, the team at NJIT will continue to assist and work on directed documents as directed by Rutgers and FHWA.

# Changes /Problems

None.

# Participants & charged Level of Efforts

|  |  |  |  |
| --- | --- | --- | --- |
| **Personnel Name** | **Role/Contribution** | **Total Hours** | **Billed Cost** |
| Aaron Strand | Technician | 3.5 | $69/hour |
| Matthew Bandelt | Project Engineer | 14 | $127/hour |
| Matthew Adams | Project Engineer | 14 | $127/hour |
| Mandeep Pokhrel | Technician | 16 | $69/hour |

|  |  |  |  |
| --- | --- | --- | --- |
| Task 2 | Task 3 | Task 4 | Total |
| 47.6 | 0 | 0 | 47.6 hrs |

# Travel

None.