**Federal Contract # DTFH61-17D00001 – Task Order #2**

**LONG-TERM BRIDGE PERFORMANCE PROGRAM**

PROGRESS REPORT NO. 11

Report Period: September 1, 2018 – September 30, 2018

Prepared For:

**Federal Highway Administration**

Prepared By:



**A. Account of work performed in this period**

* 1. **Coordination and Meetings Between the Contractor and FHWA LTBP Team**

The Rutgers team had a few correspondences with the FHWA team over the phone or by email. Furthermore, the Rutgers team had a web conference with the FHWA team on September 24th.

Co-PI: 7.5 hour

Program Manager: 8 hours

* 1. **Develop LTBP Program bridge performance strategic research matrix**

In the month of September, work continued on the strategic research application (Task 2.3) presented to and approved by FHWA on June 20th, 2018. It is estimated that Task 2.3 is 80% complete at this time. Subtasks and their percent completion are as follows:

Task 2.3.1 – *Develop/finalize pipeline for automated data retrieval and storage* (90% Complete):

A working pipeline for data retrieval from the TRID database has been developed. In the month of July, the Rutgers team investigated an additional data source (National Transportation Library) per a suggestion from FHWA on the June 20th meeting. It was determined that NTL provided little additional information and therefore would not be included in the SRMs, however, it should be noted that development of a pipeline for data retrieval from NTL is feasible if it is decided this resource should be included in future versions of the SRM application.

Task 2.3.2 – *Create the SRM database schema to store research project data* (100% Complete):

At this time, this task is complete. It is anticipated that any additional work on this task will include the refinement of database schema for any additional data sources that may be requested.

Task 2.3.3 – *Populate SRM database using data retrieval/storage pipeline* (100% Complete):

At this time, this task is complete. It is anticipated that any additional work on this task will include the refinement of database schema for any additional data sources that may be requested.

Task 2.3.4a – *Identify all known current and planned research efforts related to bridge performance research topic areas* (Ongoing, 30% Complete):

Work on this task began in June with the development of the proof of concept SRM application that was presented to FHWA on June 20th, 2018. This task will progress concurrently with the development of the proposed SRM application.

Task 2.3.4b – *Create frontend interface to visualize and explore the data collected and stored in the SRM database* (80% Complete):

A proof of concept web interface was presented to FHWA on June 20th which received positive feedback and approval from FHWA to move forward. Work in the month of September included further development of the SRM interface as per the implementation strategy proposed. A working interface was presented to FHWA during the web conference held on Monday October 24th.

Program Manager: 8 hours

Staff Engineer: 150 hours

Technician: 16.88 hours

Project Support: 13.5 hours

* 1. **Conduct training for all field personnel on LTBP Protocols**

Nothing was done during this period.

* 1. **Development of data collection protocols and RABIT-CE operations manual**

Nothing was done during this period.

* 1. **Legacy Data Mining data extraction**

Nothing was done during this period.

* 1. **Organize, conduct, and participate in LTBP workshops and meetings**

Nothing was done during this period.

* 1. **Publications, website, communications, and technical assistance**

The Rutgers team prepared the electronic version of the monthly progress report and submitted it to FHWA. Moreover, the Rutgers team developed a MS Project file showing the project milestone and submitted it to FHWA.

Additionally, during this month, Dr. Babanejad worked on enhancing the quality of the NDT data, which was collected throughout the LTBP program, the following details this effort.

Creating Analyzed Excel Files for NDT Test Results – The first version of the analyzed data was delivered to COR. The analyzed excel files were created for Mid-Atlantic cluster bridges during 2013, 2015, and 2017. This task was completed 100% in September.

Reprocessing the Problematic Test Results – Some of the NDT test results were skeptical. This activity was started in July, however, it continued to September. Over 90% of this task was completed by the end of September. From almost 280 tests, 7% of those were identified to be problematic. Due to the uncertainties associated with debugging the problematic test results, the exact timeline for this task could not be set perfectly.

Co-PI: 29.5 hours

Program Manager: 10 hours

Staff Engineer: 100.5 hours

Technician: 75

Project Support: 19.5 hours

**B. Work to be accomplished during the next period**

* 1. **Coordination and Meetings Between the Contractor and FHWA LTBP Team**

The Rutgers team will meet with reach out to FHWA to set up a meeting for the month of October.

* 1. **Develop LTBP Program bridge performance strategic research matrix**

Work efforts in the month of October will continue for Task 2.3.4: (a) implementation and refinement of queries to the SRM database for searching and classifying all known current and planned research efforts (projects and publications), and (b) implementing interface components (as needed) in order to satisfy the objectives of SRM task. The SRM web application will be tested and made available to FHWA for review.

* 1. **Conduct training for all field personnel on LTBP Protocols**

No work is planned under this task for the next reporting period.

* 1. **Development of data collection protocols and RABIT-CE operations manual**

No work is planned under this task for the next reporting period.

* 1. **Legacy Data Mining data extraction**

No work is planned under this task for the next reporting period.

* 1. **Organize, conduct, and participate in LTBP workshops and meetings**

No work is planned under this task for the next reporting period.

* 1. **Publications, website, communications, and technical assistance**

The Rutgers team will prepare the electronic version of the monthly progress report and will submit it to FHWA. Moreover, the Rutgers team will submit the updated MS Project file to FHWA.

.

**C. Problems/Recommended Solutions**

The Rutgers team is still waiting to receive comments from the COR for the report submitted for task 4 (protocols). Due to not receiving the comments/feedback from the COR, there will be delays in the delivery of this task.

**D. How the results of the work performed supports one or more of the FHWA, DOT and LTBP Goals**

The following is a summary of how the work performed on the primary tasks of this task order contribute to meeting the FHWA, DOT, and LTBP program goals.

**Task 2 - Develop LTBP Program bridge performance strategic research matrix**

Fundamentally, the SRMs aim to link the LTBP program to the larger research community. By placing the LTBP efforts in this larger context, the program will be able to identify potential synergies and collaborative opportunities as well as any overlaps that may exist. This will both increase the cost effectiveness of the program as well as the program’s impact on bridge engineering practice through clearly showing how the LTBP program contributes to the overall bridge performance research landscape.

**Task 3 - Conduct training for all field personnel on LTBP Protocols**

At the heart of the LTBP program’s data collection effort is the requirement that data be obtained in a consistent and reliable manner across the breadth of the program. Variations in collection techniques or unreliable practices would pollute the data streams and greatly limit the ability of the program to meets its goal of improving our understanding of long-term bridge performance. Activities under this task aim to ensure that the data collection efforts of the LTBP program are executed by teams with the required expertise to obtain consistent and reliable data.

**Task 4 - Development of data collection protocols and RABIT-CE operations manual**

Similar to the training work being conducted under Task 3, this task is also involved in ensuring consistent and reliable data collection throughout the program. Specifically, this task will develop additional protocols and operations manuals that specify best-practice approaches for data collection.

**Task 5 - Legacy Data Mining data extraction**

In addition to ensuring consistent and reliable data collection efforts, the overarching goal of the program is also dependent upon the completeness of the data collection efforts. This task contributes to this through the collection of available legacy data. This data not only provides a means to ensure field data collection efforts are carried out efficiently (i.e. on bridges best suited to meeting the program’s goals) but also provides context to the data to help explain observed trends and correlations (and thus further our understanding of long-term bridge performance).

**E. Purchases and Rentals**

Nothing was purchased during this period.

**F. Travel Details for Reporting Period**

None.

**G. Current and Cumulative Expenditures (cost shown includes benefits and overhead)**

|  |  |  |
| --- | --- | --- |
| **Institution** | **Current Expenditures**  **9/1/2018 – 9/30/2018** | **Cumulative Expenditures**  **10/1/2017 – 9/30/2018** |
| Rutgers, the State University of New Jersey | $ 33,779.00 | $ 741,361.59 |
| Bridge Intelligence LLC | $ 4,810.00 | $ 73,001.39 |
| Pennoni Associates | $ 0 | $ 33,138.00 |
| Infratek Solutions | $ 0 | $ 25,244.00 |
| New Jersey Institute of Technology | $ 1,164.72 | $ 22,833.10 |

**H. Subcontractor’s Progress Report**