## Schedule
| July |  |  | August
| Week 3 | Week 4 | Week 5 | Week 1 | Week 2 | Week 3 | Week 4
Tasks | 2019-07-15 | 2019-07-22 | 2019-07-29 | 2019-08-05 | 2019-08-12 | 2019-08-19 | 2019-08-26
Build and Error Screen Fiber Model (Steel Beam) | bar: 2019-07-15
Build and Error Screen Fiber Model (Prestressed Concrete) | bar: 2019-07-22
Build FE model of steel multigirder bridge | bar: 2019-07-29
Build FE model of prestressed bridge | bar: 2019-07-29
Perform sensitivity studies with fiber models (moment curvature)
Deck delamination | bar: 2019-07-29
Localized reduced modulus | bar: 2019-07-29
Loss of composite action | bar: 2019-08-05
Girder section loss | bar: 2019-08-12
Perform sensitivity studies with FE models (load distribution)
Deck delamination | bar: 2019-08-12
Localized reduced modulus | bar: 2019-08-12
Loss of composite action | bar: 2019-08-19
Girder section loss | bar: 2019-08-26
Evaluate effect of degredation on load ratings | bar: 2019-08-26

## Schedule (3)
Tasks | July | August | September | October | November | December
Build and Error Screen Fiber Model (Steel Beam) | bar: July
Build and Error Screen Fiber Model (Prestressed Concrete) | bar: August
Build FE model of steel multigirder bridge | bar: August
Build FE model of prestressed bridge | bar: August
Perform sensitivity studies with fiber models (moment curvature)
Deck delamination | bar: August
Loss of composite action | bar: September
Loss of strands | bar: September
Process and interpret data | bar: September
Perform sensitivity studies with FE models (load distribution)
Deck delamination | bar: October
Localized reduced modulus | bar: October
Loss of composite action | bar: October
Loss of strands | bar: October
Process and interpret data | bar: November
Evaluate effect of degredation on load ratings
Select case structures with appropriate field data | bar: November
Incorporate field data into demand models | bar: November
Incorporate field data into capacity models | bar: November
Process and intepret data | bar: November
Report on findings | bar: December

## Schedule (2)
Tasks | July | August | September | October | November | December
Build and Error Screen Fiber Model (Steel Beam) | bar: July
Build and Error Screen Fiber Model (Prestressed Concrete) | bar: August
Build FE model of steel multigirder bridge | bar: August
Build FE model of prestressed bridge | bar: August
Perform sensitivity studies with fiber models (moment curvature)
Deck delamination | bar: August
Localized reduced modulus | bar: August
Loss of composite action | bar: September
Girder section loss | bar: September
Process and interpret data | bar: September
Perform sensitivity studies with FE models (load distribution)
Deck delamination | bar: October
Localized reduced modulus | bar: October
Loss of composite action | bar: October
Girder section loss | bar: October
Process and interpret data | bar: November
Evaluate effect of degredation on load ratings
Select case structures with appropriate field data | bar: November
Incorporate field data into demand models | bar: November
Incorporate field data into capacity models | bar: November
Process and intepret data | bar: November
Report on findings | bar: December

## Time
Tasks | Days
Build and Error Screen Fiber Model (Steel Beam) | 3
Build and Error Screen Fiber Model (Prestressed Concrete) | 2
Build FE model of steel multigirder bridge | 1
Build FE model of prestressed bridge | 1
Perform sensitivity studies with fiber models (moment curvature) | 3
Deck delamination | 0.5
Localized reduced modulus | 0.5
Loss of composite action | 1
Girder section loss | 1
Perform sensitivity studies with FE models (load distribution) | 5
Deck delamination | 1
Localized reduced modulus | 1
Loss of composite action | 1
Girder section loss | 1
Evaluate effect of degredation on load ratings | 3
Total | 18